## Upload
Step | Task Name | Location | Task Type | FKClientID | FKProjectID | TaskDate | TaskLink | AssignTo | ysnSubTask | FKParentID | Duration | Priority
1 | Send Kickoff Memo (with PQ) |  | EA |  |  |  | 0 | non-engineer | TRUE |  | 1
2 | Request Tenant Contact List with Square Footages |  | EA |  |  |  | 0 | non-engineer | TRUE |  | 1
3 | Request 1 Month of Utility Bills from Tenant |  | EA |  |  |  | 0 | non-engineer | TRUE |  | 1
4 | Receive and import PLQ and PBQ responses. (0tblIPA) |  | EA |  |  |  | 1 | non-engineer | TRUE |  | 5
5 | Receive Tenant Contact List with Square Footages |  | EA |  |  |  | 2 | non-engineer | TRUE |  | 5
6 | Receive 1 Month of Utility Bills from Tenant |  | EA |  |  |  | 3 | non-engineer | TRUE |  | 5
7 | Send Pre-inspection kickoff memo to tenants what to expect from Energy Audit Memo to Tenants |  | EA |  |  |  | 5 | non-engineer | TRUE |  | 3
8 | Schedule Audit Inspection |  | EA |  |  |  | 1,2,3,4,5,6 | non-engineer | TRUE |  | 5
9 | Schedule HVAC contractor on day of inspection. |  | EA |  |  |  | 1,2,3,4,5,6 | non-engineer | TRUE |  | 5
10 | Review PQ Before Inspection |  | EA |  |  |  | 1,2,3,4,5,6 | engineer | TRUE |  | 5
11 | Prep list of building questions for walkthrough kickoff |  | EA |  |  |  | 1,2,3,4,5,6 | engineer | TRUE |  | 5
12 | Prep list of questions for HVAC contractor. |  | EA |  |  |  | 1,2,3,4,5,6 | engineer | TRUE |  | 5
13 | Energy Audit Walkthrough |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12 | engineer | TRUE |  | 1
14 | HVAC Contractor Walkthrough |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12 | engineer | TRUE |  | 1
15 | Scan Energy Audit Notes - Upload to Gdrive |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,14 | non-engineer | TRUE |  | 3
16 | List of EEM Ideas from Walkthrough |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,14 | engineer | TRUE |  | 3
17 | Download Pictures |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,14 | non-engineer | TRUE |  | 3
18 | Group Pictures by Occupant |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,14 | non-engineer | TRUE |  | 3
19 | Benchmarking Bill Analysis / Aggregation - (w/ benchmarking only) |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,14 | non-engineer | TRUE |  | 5
20 | Follow-Up Questions Memo |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,14 | engineer | TRUE |  | 5
21 | Add to 1tblProject |  | EA |  |  |  | 1 | non-engineer | TRUE |  | 5
22 | Verify/Add to tlkUtilityRates |  | EA |  |  |  | 1,3,6 | non-engineer | TRUE |  | 5
23 | Add to 2tblOccupants |  | EA |  |  |  | 1,2,5 | non-engineer | TRUE |  | 5
24 | Add to tlkSchBase |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13 | non-engineer | TRUE |  | 5
25 | Add to tlkSchProp |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13 | non-engineer | TRUE |  | 5
26 | Add to tlkFinancials |  | EA |  |  |  | 1,4 | non-engineer | TRUE |  | 5
27 | Create EID excel sheet Start inputting data from template |  | EA |  |  |  | 1 | non-engineer | TRUE |  | 5
28 | Type in Space Descriptions |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13 | engineer | TRUE |  | 3
29 | Assign EIDqtyBase |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13 | engineer | TRUE |  | 3
30 | Assign EIDqtyProp |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13 | engineer | TRUE |  | 3
31 | Assign tlkFinances |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,28 | non-engineer | TRUE |  | 5
32 | Assign tlkLightCodes (Add if necessary) |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,28 | engineer | TRUE |  | 5
33 | Assign schBaseID Codes |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,28 | engineer | TRUE |  | 5
34 | Assign schPropID Codes |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,28 | engineer | TRUE |  | 5
35 | Enter EIDyrsInstalled (See PBQ or audit notes) |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,28 | engineer | TRUE |  | 5
36 | Assign lightSpaceTypeID (from tlkOccSensorSavings) |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,28 | engineer | TRUE |  | 5
37 | Assign EEMs to 3tblEID (Add if necessary) |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,28 | engineer | TRUE |  | 5
38 | Assign tlkIncentives (Add if neccessary) |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,28 | engineer | TRUE |  | 5
39 | Lighting Occupancy Sensor Projects |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,28 | engineer | TRUE |  | 5
40 | Upload 3tblEID into MS Access file. |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37 | non-engineer | TRUE |  | 1
41 | Google Picture of HVAC Equipment on Roof |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,14 | engineer | TRUE |  | 5
42 | Add tlkHVACcodes |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,14 | non-engineer | TRUE |  | 5
43 | Create HAVC EIDs in Excel File |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,14,42 | non-engineer | TRUE |  | 3
44 | Complete Trane Models |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,14 | engineer | TRUE |  | 5
45 | Add HVAC Code EEMs List |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,14,42,43 | engineer | TRUE |  | 3
46 | Upload HVAC EIDs into Access |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,14,42,43,44,45 | non-engineer | TRUE |  | 1
47 | Enter HVAC Photos |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,14,42,43,44,45,46 | non-engineer | TRUE |  | 3
48 | Punch List Completed |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,14,42,43,44,45,46 | engineer | TRUE |  | 3
49 | Run Access Report Sucessfully |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40 | non-engineer | TRUE |  | 1
50 | Review for negative NPVs - Create No Project |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40,49 | non-engineer | TRUE |  | 1
51 | rptImagesHVCD |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,14,42,43,44,45,46,47 | non-engineer | TRUE |  | 1
52 | Energy Audit Savings to Consumption Ratio - (w/ benchmarking only) |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40,49,14,19, 50 | non-engineer | TRUE |  | 1
53 | QC Savings Calcs |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40,49,50 | engineer | TRUE |  | 3
54 | Report Presentation Scheduled |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40,49,50,53 | engineer | TRUE |  | 1
55 | Submit projects to SF Environment |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40,49,50,53 | non-engineer | TRUE |  | 3
56 | Assumptions Report |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40,49,50 | non-engineer | TRUE |  | 3
57 | Equipment Cut Sheets |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,28,42 | non-engineer | TRUE |  | 3
58 | Consumption Summary |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,14,42,43,44,45,46,48 | non-engineer | TRUE |  | 3
59 | Building Best Practices |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,14,42,43,44,45,46,48 | non-engineer | TRUE |  | 3
60 | Operations / Low Cost /No Cost Report |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,14,42,43,44,45,46,48 | non-engineer | TRUE |  | 3
61 | Tenant Benefits Report |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40,49,50,53 | non-engineer | TRUE |  | 3
62 | Non-Financial Benefits Report |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40,49,50,53 | non-engineer | TRUE |  | 3
63 | Non-Utility Benefits |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,28,37 | non-engineer | TRUE |  | 5
64 | Executive Summary |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40,49,50,53 | non-engineer | TRUE |  | 3
65 | Post Audit Survey |  | EA |  |  |  | 1 | Bookkeeper | TRUE |  | 14
66 | Invoice |  | EA |  |  |  | 1 | Bookkeeper | TRUE |  | 14
67 | Complete Deliverables Checklist |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,27,28,29,30,31,32,33,34,35,36,37,40,42,43,44,45,46,48,49,50,53 | non-engineer | TRUE |  | 1
68 | Create PDF |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,27,28,29,30,31,32,33,34,35,36,37,40,42,43,44,45,46,48,49,50,53 | non-engineer | TRUE |  | 1
69 | Print |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,27,28,29,30,31,32,33,34,35,36,37,40,42,43,44,45,46,48,49,50,53 | non-engineer | TRUE |  | 1
70 | Binding and Layout |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,27,28,29,30,31,32,33,34,35,36,37,40,42,43,44,45,46,48,49,50,53 | non-engineer | TRUE |  | 1
71 | Final Report Presented |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,27,28,29,30,31,32,33,34,35,36,37,40,42,43,44,45,46,48,49,50,53,67,68,69,70 | engineer | TRUE |  | 1
72 | Final Report Completed |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,27,28,29,30,31,32,33,34,35,36,37,40,42,43,44,45,46,48,49,50,53,67,68,69,70 | engineer | TRUE |  | 1
73 | Update Energy Audit Results Summary |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,27,28,29,30,31,32,33,34,35,36,37,40,42,43,44,45,46,48,49,50,53,54,55,56,57,58,59,60,61,62,63,64,65,66,67,68,69,70 | Bookkeeper | TRUE |  | 5
74 | Receive Post Audit Survey |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,27,28,29,30,31,32,33,34,35,36,37,40,42,43,44,45,46,48,49,50,53,67,68,69,70,71 | Bookkeeper | TRUE |  | 5
75 | Receive Payment |  | EA |  |  |  | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,27,28,29,30,31,32,33,34,35,36,37,40,42,43,44,45,46,48,49,50,53,67,68,69,70,72 | Bookkeeper | TRUE |  | 22

## Proposal
| Before Client Intake | Notes:
1 | Client Phone Call
2 | Download MLS Sheet or Loopnet Sheet |  | Ty
3 | Fill Out Proposal Form |  | Ty
4 | Create a new account number and folder name in the client folder: |  | JJ
5 | Generate Proposal |  | JJ
6 | Create Cover Letter |  | JJ
5 | QC Proposal |  | Ty
6 | Send Proposal |  | Ty
7 | Follow Up with Proposal |  |  | Can there be an or statement where we do follow-up or we do send contract.
Client Intake
Create a new folder in the client folder
8 | Move the client from proposal folder into the clients folder (i.e. 7007 – Contract Company Name – Building Address) | Google Drive\bay efficiency\7000 - Clients (JCB, Linda)
Create contract
9 | Copy contract into client folder: Google Drive\bay efficiency\1 - Admin\Energy Audits\1 - Procedures\Proposal Procedures
10 | Rename file name with client name and bay efficiency
11 | Update fields on page 4
12 | Hit F9 to update bookmarks
13 | Save and PDF contract- (only contract pages)
Create invoice for deposit in freshbooks
14 | Create new customer in freshbooks | https://bayefficiency.freshbooks.com/viewUser
15 | Create an invoice for the deposit- save as PDF in client folder
Email client with contract and deposit invoice
16 | Insert cover email from notes | Cover letter: Bay Efficiency is pleased to offer you this benchmarking contract. I trust this contract meets your expectations. If not, please contact me so that we can tailor it to your expectations. If acceptable, please sign below and return. Please let me know if you have any questions or comments. We look forward to working with you on this exciting project. I have attached Bay Efficiency, LLC ‘s proof of insurance and W-9.
17 | Get contract QA from Ty
18 | Attach final PDF contract | Google Drive\bay efficiency\1 - Admin\Energy Audits\1 - Procedures\Proposal Procedures
19 | Attach documents from attachments folder- proof of insurance and w-9
20 | Attach invoice for deposit
Create new CRM contact from the customers form
21 | Create new customer and enter all fields
Receive the signed contract and deposit check
22 | File signed contract into client folder
23 | Mark payment in freshbooks
24 | Deposit check
25 | Send client receipt
Notify SF Enviornment if required
26 | https://docs.google.com/a/bayefficiency.com/spreadsheet/viewform?formkey=dFVXbkFVaG1zcDJHc19xNTRyZHVJRkE6MQ
Insert Proper Folder Heirarchy
27 | Create a Copy of Audit Template Folder and Paste into Client Folder.
After Client Intake
28 | Launch Benchmarking and Energy Audit

## Benchmarking
1 | Send Kickoff Email | 2014-02-01 | 1 | 2014-02-03 |  | Non-engineer | Update - Form Assembly form no longer sends tenant to PG&E website for Data Authorization. Must create PM account first
2 | Receive Tenant List, Receive Account Meter List | #REF! | 7 | #REF! | 3 | Non-engineer
3 | Receive Completed Form Assembly forms
4 | Fill out shared Benchmarking Required Info Gsheet with all of the information that we have.
5 | Phone interview - Owner/Property Manager - to verify meters and space end uses. Phone call review which spaces did not fill out the form. Introduce gsheet for them to track.
6 | Receive all missing meter and PG&E account information | #REF! | 7 | #REF! | 2,4 | Non-engineer
7 | Create Portfolio Manager Account | 2014-02-03 | 1 | 2014-02-04 | 1 | Non-engineer
8 | Add two contacts: PG&E Benchmarking & benchmarking@bayefficiency.com
9 | Create a copy of the Portfolio Manager Upload Form | 2014-02-01 | 1 | 2014-02-03 | 1 | Non-engineer | Compare info in benchmarking_form with completed tenant list, note any discrepancies
10 | Complete Properties Tab | #REF! | 1 | #REF! | 4,5,6 | Non-engineer
11 | Complete Unique Identifiers Tab | #REF! | 1 | #REF! | 4,5,6 | Non-engineer
12 | Complete Uses Tab | #REF! | 1 | #REF! | 4,5,6 | Non-engineer | including vacant spaces
13 | Complete Parking Tab | #REF! | 1 | #REF! | 4,5,6 | Non-engineer
14 | Complete Swimming Pool Tab | #REF! | 1 | #REF! | 4,5,6 | Non-engineer
15 | Upload Add_New_Properties to Portfolio Manager | #REF! | 3 | #REF! | 11,12,13,14,15,16,17,18 | Non-engineer
16 | Fill in Space Use Detail on Portfolio Manager Website
17 | Create Custom Meter Form - Upload 2 | #REF! | 1 | #REF! | 10,11,12,20 | Non-engineer
18 | Copy Meters from Tenant/Meter online list and PG&E meter data | #REF! | 1 | #REF! | 10,11,12,20,21 | Non-engineer
19 | Upload custom Meter form to Portfolio Manager | #REF! | 1 | #REF! | 22 | Non-engineer
20 | Authorize all Account numbers associated with the building on PG&E website
21 | Share building with PG&E, set up data exchange
22 | Run Data Quality Checker | #REF! | 1 | #REF! | 24,25 | Engineer
23 | Fix all error alerts | #REF! | 1 | #REF! | 26 | Engineer
24 | Verify that either an Energy Star score or EUI is populated | #REF! | 1 | #REF! | 26 | Engineer
25 | Update property notes for any unique situations | #REF! | 1 | #REF! | 26 | Engineer
26 | Print out SEPs | #REF! | 1 | #REF! | 27,28,29 | Non-engineer
27 | Send information: AB1103 to CEC - SF to SF Environment | #REF! | 1 | #REF! | 27,28,29 | Non-engineer
28 | Create Invoice | 2014-02-03 | 7 | 2014-02-12 | 1 | Bookkeeper
29 | QA | #REF! | 2 | #REF! | 29,30,31 | Engineer
30 | Create Cover Letter | #REF! | 1 | #REF! | 39
31 | Deliver Report | #REF! | 1 | #REF! | 33 | Non-engineer
32 | SF Only - Receive confirmation from SF Environment | #REF! | 7 | #REF! | 37 | Non-engineer
33 | Update Tracking Summary | #REF! | 5 | #REF! | 41,42 | Bookkeeper
34 | Receive Payment | #REF! | 22 | #REF! | 41 | Bookkeeper

## Energy Audit
1 | Send Kickoff Memo (with PQ) | 2014-02-01 | 1 | 2014-02-03 |  | 0 | non-engineer
2 | Request Tenant Contact List with Square Footages | 2014-02-01 | 1 | 2014-02-03 |  | 0 | non-engineer
3 | Request 1 Month of Utility Bills from Tenant | 2014-02-01 | 1 | 2014-02-03 |  | 0 | non-engineer
4 | Receive and import PLQ and PBQ responses. (0tblIPA) | 2014-02-03 | 5 | 2014-02-10 | 1 | 1 | non-engineer
5 | Receive Tenant Contact List with Square Footages | 2014-02-03 | 5 | 2014-02-10 | 2 | 2 | non-engineer
6 | Receive 1 Month of Utility Bills from Tenant | 2014-02-03 | 5 | 2014-02-10 | 3 | 3 | non-engineer
7 | Send Pre-inspection kickoff memo to tenants what to expect from Energy Audit Memo to Tenants | 2014-02-10 | 3 | 2014-02-13 | 5 | 5 | non-engineer
8 | Schedule Audit Inspection | 2014-02-10 | 5 | 2014-02-17 | 4,5,6 | 1,2,3,4,5,6 | non-engineer
9 | Schedule HVAC contractor on day of inspection. | 2014-02-10 | 5 | 2014-02-17 | 4,5,6 | 1,2,3,4,5,6 | non-engineer
10 | Review PQ Before Inspection | 2014-02-10 | 5 | 2014-02-17 | 4,5,6 | 1,2,3,4,5,6 | engineer
11 | Prep list of building questions for walkthrough kickoff | 2014-02-10 | 5 | 2014-02-17 | 4,5,6 | 1,2,3,4,5,6 | engineer
12 | Prep list of questions for HVAC contractor. | 2014-02-10 | 5 | 2014-02-17 | 4,5,6 | 1,2,3,4,5,6 | engineer
13 | Energy Audit Walkthrough | 2014-02-17 | 1 | 2014-02-18 | 7,8,9,10,11,12 | 1,2,3,4,5,6,7,8,9,10,11,12 | engineer
14 | HVAC Contractor Walkthrough | 2014-02-17 | 1 | 2014-02-18 | 7,8,9,10,11,12 | 1,2,3,4,5,6,7,8,9,10,11,12 | engineer
15 | Scan Energy Audit Notes - Upload to Gdrive | 2014-02-18 | 3 | 2014-02-21 | 13,14 | 1,2,3,4,5,6,7,8,9,10,11,12,13,14 | non-engineer
16 | List of EEM Ideas from Walkthrough | 2014-02-18 | 3 | 2014-02-21 | 13,14 | 1,2,3,4,5,6,7,8,9,10,11,12,13,14 | engineer
17 | Download Pictures | 2014-02-18 | 3 | 2014-02-21 | 13,14 | 1,2,3,4,5,6,7,8,9,10,11,12,13,14 | non-engineer
18 | Group Pictures by Occupant | 2014-02-18 | 3 | 2014-02-21 | 13,14 | 1,2,3,4,5,6,7,8,9,10,11,12,13,14 | non-engineer
19 | Benchmarking Bill Analysis / Aggregation - (w/ benchmarking only) | 2014-02-18 | 5 | 2014-02-25 | 13,14 | 1,2,3,4,5,6,7,8,9,10,11,12,13,14 | non-engineer
20 | Follow-Up Questions Memo | 2014-02-18 | 5 | 2014-02-25 | 13,14 | 1,2,3,4,5,6,7,8,9,10,11,12,13,14 | engineer
21 | Add to 1tblProject | 2014-02-01 | 5 | 2014-02-07 | 1 | 1 | non-engineer
22 | Verify/Add to tlkUtilityRates | 2014-02-10 | 5 | 2014-02-17 | 6 | 1,3,6 | non-engineer
23 | Add to 2tblOccupants | 2014-02-10 | 5 | 2014-02-17 | 5 | 1,2,5 | non-engineer
24 | Add to tlkSchBase | 2014-02-18 | 5 | 2014-02-25 | 13 | 1,2,3,4,5,6,7,8,9,10,11,12,13 | non-engineer
25 | Add to tlkSchProp | 2014-02-18 | 5 | 2014-02-25 | 13 | 1,2,3,4,5,6,7,8,9,10,11,12,13 | non-engineer
26 | Add to tlkFinancials | 2014-02-10 | 5 | 2014-02-17 | 4 | 1,4 | non-engineer
27 | Create EID excel sheet Start inputting data from template | 2014-02-01 | 5 | 2014-02-07 | 1 | 1 | non-engineer
28 | Type in Space Descriptions | 2014-02-18 | 3 | 2014-02-21 | 13 | 1,2,3,4,5,6,7,8,9,10,11,12,13 | engineer
29 | Assign EIDqtyBase | 2014-02-18 | 3 | 2014-02-21 | 13 | 1,2,3,4,5,6,7,8,9,10,11,12,13 | engineer
30 | Assign EIDqtyProp | 2014-02-18 | 3 | 2014-02-21 | 13 | 1,2,3,4,5,6,7,8,9,10,11,12,13 | engineer
31 | Assign tlkFinances | 2014-02-21 | 5 | 2014-02-28 | 28 | 1,2,3,4,5,6,7,8,9,10,11,12,13,28 | non-engineer
32 | Assign tlkLightCodes (Add if necessary) | 2014-02-21 | 5 | 2014-02-28 | 28 | 1,2,3,4,5,6,7,8,9,10,11,12,13,28 | engineer
33 | Assign schBaseID Codes | 2014-02-21 | 5 | 2014-02-28 | 28 | 1,2,3,4,5,6,7,8,9,10,11,12,13,28 | engineer
34 | Assign schPropID Codes | 2014-02-21 | 5 | 2014-02-28 | 28 | 1,2,3,4,5,6,7,8,9,10,11,12,13,28 | engineer
35 | Enter EIDyrsInstalled (See PBQ or audit notes) | 2014-02-21 | 5 | 2014-02-28 | 28 | 1,2,3,4,5,6,7,8,9,10,11,12,13,28 | engineer
36 | Assign lightSpaceTypeID (from tlkOccSensorSavings) | 2014-02-21 | 5 | 2014-02-28 | 28 | 1,2,3,4,5,6,7,8,9,10,11,12,13,28 | engineer
37 | Assign EEMs to 3tblEID (Add if necessary) | 2014-02-21 | 5 | 2014-02-28 | 28 | 1,2,3,4,5,6,7,8,9,10,11,12,13,28 | engineer
38 | Assign tlkIncentives (Add if neccessary) | 2014-02-21 | 5 | 2014-02-28 | 28 | 1,2,3,4,5,6,7,8,9,10,11,12,13,28 | engineer
39 | Lighting Occupancy Sensor Projects | 2014-02-21 | 5 | 2014-02-28 | 28 | 1,2,3,4,5,6,7,8,9,10,11,12,13,28 | engineer
40 | Upload 3tblEID into MS Access file. | 2014-02-28 | 1 | 2014-03-03 | 27,29,30,31,32,33,34,35,36,37 | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37 | non-engineer
41 | Google Picture of HVAC Equipment on Roof | 2014-02-18 | 5 | 2014-02-25 | 14 | 1,2,3,4,5,6,7,8,9,10,11,12,14 | engineer
42 | Add tlkHVACcodes | 2014-02-18 | 5 | 2014-02-25 | 14 | 1,2,3,4,5,6,7,8,9,10,11,12,14 | non-engineer
43 | Create HAVC EIDs in Excel File | 2014-02-25 | 3 | 2014-02-28 | 42 | 1,2,3,4,5,6,7,8,9,10,11,12,14,42 | non-engineer
44 | Complete Trane Models | 2014-02-18 | 5 | 2014-02-25 | 14 | 1,2,3,4,5,6,7,8,9,10,11,12,14 | engineer
45 | Add HVAC Code EEMs List | 2014-02-28 | 3 | 2014-03-05 | 43 | 1,2,3,4,5,6,7,8,9,10,11,12,14,42,43 | engineer
46 | Upload HVAC EIDs into Access | 2014-03-05 | 1 | 2014-03-06 | 44,45 | 1,2,3,4,5,6,7,8,9,10,11,12,14,42,43,44,45 | non-engineer
47 | Enter HVAC Photos | 2014-03-06 | 3 | 2014-03-11 | 46 | 1,2,3,4,5,6,7,8,9,10,11,12,14,42,43,44,45,46 | non-engineer
48 | Punch List Completed | 2014-03-06 | 3 | 2014-03-11 | 46 | 1,2,3,4,5,6,7,8,9,10,11,12,14,42,43,44,45,46 | engineer
49 | Run Access Report Sucessfully | 2014-03-03 | 1 | 2014-03-04 | 40 | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40 | non-engineer
50 | Review for negative NPVs - Create No Project | 2014-03-04 | 1 | 2014-03-05 | 49 | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40,49 | non-engineer
51 | rptImagesHVCD | 2014-03-11 | 1 | 2014-03-12 | 47 | 1,2,3,4,5,6,7,8,9,10,11,12,14,42,43,44,45,46,47 | non-engineer
52 | Energy Audit Savings to Consumption Ratio - (w/ benchmarking only) | 2014-03-05 | 1 | 2014-03-06 | 19, 50 | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40,49,14,19, 50 | non-engineer
53 | QC Savings Calcs | 2014-03-05 | 3 | 2014-03-10 | 50 | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40,49,50 | engineer
54 | Report Presentation Scheduled | 2014-03-10 | 1 | 2014-03-11 | 53 | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40,49,50,53 | engineer
55 | Submit projects to SF Environment | 2014-03-10 | 3 | 2014-03-13 | 53 | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40,49,50,53 | non-engineer
56 | Assumptions Report | 2014-03-05 | 3 | 2014-03-10 | 50 | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40,49,50 | non-engineer
57 | Equipment Cut Sheets | 2014-02-28 | 3 | 2014-03-05 | 35, 43 | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,28,42 | non-engineer
58 | Consumption Summary | 2014-03-11 | 3 | 2014-03-14 | 48 | 1,2,3,4,5,6,7,8,9,10,11,12,14,42,43,44,45,46,48 | non-engineer
59 | Building Best Practices | 2014-03-11 | 3 | 2014-03-14 | 48 | 1,2,3,4,5,6,7,8,9,10,11,12,14,42,43,44,45,46,48 | non-engineer
60 | Operations / Low Cost /No Cost Report | 2014-03-11 | 3 | 2014-03-14 | 48 | 1,2,3,4,5,6,7,8,9,10,11,12,14,42,43,44,45,46,48 | non-engineer
61 | Tenant Benefits Report | 2014-03-10 | 3 | 2014-03-13 | 53 | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40,49,50,53 | non-engineer | Add
62 | Non-Financial Benefits Report | 2014-03-10 | 3 | 2014-03-13 | 53 | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40,49,50,53 | non-engineer | post audit survey
63 | Non-Utility Benefits | 2014-02-28 | 5 | 2014-03-07 | 37 | 1,2,3,4,5,6,7,8,9,10,11,12,13,28,37 | non-engineer | implementation 1 page proposal
64 | Executive Summary | 2014-03-10 | 3 | 2014-03-13 | 53 | 1,2,3,4,5,6,7,8,9,10,11,12,13,27,28,29,30,31,32,33,34,35,36,37,40,49,50,53 | non-engineer
65 | Post Audit Survey | 2014-02-01 | 14 | 2014-02-20 | 1 | 1 | Bookkeeper
66 | Invoice | 2014-02-01 | 14 | 2014-02-20 | 1 | 1 | Bookkeeper
67 | Complete Deliverables Checklist | 2014-03-14 | 1 | 2014-03-17 | 54,55,56,57,58,59,60,61,62,63,64,65,66 | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,27,28,29,30,31,32,33,34,35,36,37,40,42,43,44,45,46,48,49,50,53 | non-engineer
68 | Create PDF | 2014-03-14 | 1 | 2014-03-17 | 54,55,56,57,58,59,60,61,62,63,64,65,66 | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,27,28,29,30,31,32,33,34,35,36,37,40,42,43,44,45,46,48,49,50,53 | non-engineer
69 | Print | 2014-03-14 | 1 | 2014-03-17 | '54,55,56,57,58,59,60,61,62,63,64,65,66 | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,27,28,29,30,31,32,33,34,35,36,37,40,42,43,44,45,46,48,49,50,53 | non-engineer
70 | Binding and Layout | 2014-03-14 | 1 | 2014-03-17 | '54,55,56,57,58,59,60,61,62,63,64,65,66 | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,27,28,29,30,31,32,33,34,35,36,37,40,42,43,44,45,46,48,49,50,53 | non-engineer
71 | Final Report Presented | 2014-03-17 | 1 | 2014-03-18 | 67,68,69,70 | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,27,28,29,30,31,32,33,34,35,36,37,40,42,43,44,45,46,48,49,50,53,67,68,69,70 | engineer
72 | Final Report Completed | 2014-03-17 | 1 | 2014-03-18 | 67,68,69,70 | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,27,28,29,30,31,32,33,34,35,36,37,40,42,43,44,45,46,48,49,50,53,67,68,69,70 | engineer
73 | Update Energy Audit Results Summary | 2014-03-17 | 5 | 2014-03-24 | 53,54,55,56,57,58,59,60,61,62,63,64,65,66,67,68 | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,27,28,29,30,31,32,33,34,35,36,37,40,42,43,44,45,46,48,49,50,53,54,55,56,57,58,59,60,61,62,63,64,65,66,67,68,69,70 | Bookkeeper
74 | Receive Post Audit Survey | 2014-03-18 | 5 | 2014-03-25 | 71 | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,27,28,29,30,31,32,33,34,35,36,37,40,42,43,44,45,46,48,49,50,53,67,68,69,70,71 | Bookkeeper
75 | Receive Payment | 2014-03-18 | 22 | 2014-04-17 | 72 | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,27,28,29,30,31,32,33,34,35,36,37,40,42,43,44,45,46,48,49,50,53,67,68,69,70,72 | Bookkeeper

## Exemptions
Site Visit
Take Pictures
File Exemption letter with SF Environment
Follow Up with SF Environment Exception Letter

## Implementations
implementation - capex
implementation for gross leases
Project Management | 27 | Project Schedule Made
| 28 | Bid Package Made
| 29 | Pre-Installation Incentive Walkthrough
| 29 | Companies Selected for Bid
| 30 | Bid Package Sent
| 31 | Bid Walkthrough Complete
| 32 | Company Selected | SF Environment walkthrough
| 33 | Project Started | receive incentive amounts
| 34 | Project Management Meetings | review leases
| 35 | Project Completed
| 36 | Post-Installation Incentive Walkthrough
| 37 | Post-Installation Showcase / Presentation

## New Employee
Zen Payroll
Sign up
Sign W4, I9 and Payroll Authorization
set up google drive
RDP login
part time fill out zen payroll
Sign NDA | contractor - fill out W9
Learn how to use CRM or workflow priorities R3 | get an electronic signature for NDA
create new pages in the workflow priorties document.
picture of ID
set up workflow priorities R3 pages: active, summary, timesheet, and payroll

## Benchmark Questions
Do we wait for confirmation from SF environment before we send invoice to client?